## RACI
CMMS project RACI matrix
FreeMaint Academy · How to implement a CMMS, lesson 2 · freemaint.com/academy
Yellow cells are inputs. In each task row, type R, A, C or I under each role; the Check column confirms one A and at least one R.
# | Task | Sponsor | Project lead | Key user: technicians | Key user: requesters | Key user: stores | Field champions | IT and support functions | Check
Name
1 | Set goals and record the baseline
2 | Name the project team and fill in this matrix
3 | Audit current practices and data
4 | Write the requirements list
5 | Run the trial on real assets
6 | Choose the software
7 | Build the location and asset hierarchy
8 | Define the coding rule and criticality
9 | Clean and import the data
10 | Define the request and work order flow
11 | Create the first preventive plans
12 | Set up roles and user accounts
13 | Train each role
14 | Run the pilot
15 | Go live
16 | Hold the monthly indicator review
17
18
19
20
21
22
Summary
Tasks listed
Tasks with a correct RACI
Tasks to fix
Legend
R — Responsible: does the work
A — Accountable: approves the result and answers for it (one per task)
C — Consulted: gives input beforehand
I — Informed: is told afterward

## Team
Project team
FreeMaint Academy · How to implement a CMMS, lesson 2 · freemaint.com/academy
Role | Name | Job title | Time committed (hours per week) | Contact | Notes
Sponsor
Project lead
Key user: technicians
Key user: requesters
Key user: stores
Field champions
IT and support functions
Total time committed (hours per week)