## Training plan
Role-based training plan
FreeMaint Academy · How to implement a CMMS, lesson 9 · freemaint.com/academy
Yellow cells are inputs. Train each role on what it will use, in the week before real use.
Role | What to learn | Duration (h) | Trainer | Date | Planned participants | Trained | Trained share | Notes
Requester | Report a problem with a photo or a QR code, and follow the request
Technician | Find assigned jobs; start, pause and complete them; record time, parts and cause; work offline
Planner or supervisor | Review requests, create and assign work orders, follow preventive plans and the backlog
Administrator | Users and roles, settings, imports, reports
Total

## Pilot
Pilot
FreeMaint Academy · How to implement a CMMS, lesson 9 · freemaint.com/academy
Two to four weeks on a contained scope, with no parallel paper. Meet for fifteen minutes every week.
Scope (line, building or team)
Start date
End date
Field champion
Duration (weeks)
Weekly reviews
Week | Date | What got in the way | What was slow | What was missing | Action | Owner | Done?
1
2
3
4
5
6
Exit criteria
Requests go through the CMMS without help
Work orders are completed in the CMMS, on phones
Closure records include cause, time and parts
Settings and forms adjusted after feedback
The pilot team says it would not go back
Ready to go live?

## Go-live checklist
Go-live checklist
FreeMaint Academy · How to implement a CMMS, lesson 9 · freemaint.com/academy
Check every item in the week before go-live.
Go-live date
Days to go-live
Progress
Item | Done? | Owner | Due date | Notes
Every user has an account with the right role and has logged in at least once
The app is installed on every technician's phone and works where the network is weak
Locations, assets, preventive plans, spare parts and open work orders are imported and checked
QR codes are stuck on the machines, and requesters know how to report
A champion is named in every team and shift, with time to help
The old tools have an end date: whiteboard wiped, spreadsheet archived read-only
Old records stay readable for a few weeks after go-live
Support plan for the first two weeks: who is on the floor, and when